## SSBB Batch 1&2 Tracking
Batch | S.No | Empl. ID | Participant's Name | Mobile No | Location /Unit | Department | Project Title | CTQ | UoM | Projects Baseline | Target | T.B (Annually) | A.R.S INR (Lakh) | Review Schedule (Day & Week) | D | Project Charter | VoS Template | CTQ drill Down if required | SIPROC | M | DCP | MSA | PCA | A | Stability Test | Process Analysis | Confirmation of Causes | RCI(Root cause identification) | I | Act on Root Causes | C | Collect data after improvement | Before After test of significance and test of significance against target | Capability Analysis before after | Before After Control chart and online control | Maximum Automation | Savings Estimation | Project Link
B1 | 1 | 16923 | Akram Imran | 7991162146 | Unit-I | Operations | Improve the Avg Productivity of Kiln per Month from 37.42 ton to 43 ton for Kiln1 | No of Order | Ton | 37.42 | 43 | 0 | 54.3 | Week 1 - Monday | Completed | Completed | Completed | NA | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 2 | 16923 | Akram Imran | 7991162146 | Unit-I | Operations | Improve the Avg Productivity of Kiln per Month from 36.56 ton to 43 ton for Kiln3 | Productivity | Ton | 36.56 | 43 | 0 | 62.6 | Week 1 - Monday | Completed | Completed | Completed | NA | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://drive.google.com/open?id=132BD5M24wvY9l-Gp2dkdEOvV745CFyHE&usp=drive_fs
B1 | 3 | 16923 | Akram Imran | 7991162146 | Unit-I | Operations | Improve the Avg Productivity of Kiln per Month from 37.70 ton to 43 ton for Kiln5 | Productivity | Ton | 37.7 | 43 | 0 | 51.5 | Week 1 - Monday | Completed | Completed | Completed | NA | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://drive.google.com/open?id=1ERAY9sCRPPErr_7F8dxNY-P-vgkbSgBQ&usp=drive_fs
B2 | 4 | 10223 | Amitava Dasgupta | 9330697518 | HO | DIP Marketing | Re-establish the tender data base (tender missing) ------- reducing tender processing time from ----- to ----- without adverse implication. | No of order | Nos | 0 | 0 | 0 | 0 | Week 1 - Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | https://drive.google.com/open?id=1pWWHUe27niwSw4OxsX7VJjGrpO-xIt5N&usp=drive_fs
B2 | 5 | 10860 | Souptik Mondal | 8617763687 | HO | DIP Marketing | Reducing the freight cost per Km /MT from 580 to <----. | Freight cost | Per kM/MT | 580 | 0 | 0 | 0 | Week 1 - Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 6 | 11039 | Soumen Pal | 8609908033 | HO | DIP Marketing | Re-establish the tendor data base (tendor missing) per month from -------to ----. | No of Tendor | Nos | 0 | 0 | 0 | 0 | Week 1 - Monday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 7 | 10642 | Amitava Mukherjee | 9748758581 | HO | Human Resource | Improve the Manpower engagement of HO from -- % per month to --- % per month. | 0 | 0 | 0 | 0 | 0 | 0 | Week 1 - Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 8 | 30103 | Suman Majumder | 8334936321 | ur | Operation (Chemist) | Reducing the cost of laboratory operation by optimizing chemical and machine uses . | 0 | 0 | 0 | 0 | 0 | 0 | Week 1 - Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 9 | 47015 | Aniruddha Ray | 8001385012 | Unit-IV | Accounts and Finance | Reduce the Invoice processing time of unit IV from --- to -----. | 0 | 0 | 0 | 0 | 0 | 94.34 | Week 1 - Tuesday | Completed | 0 | 0 | Completed | 0 | 0 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 10 | 4781 | Anupam Basak | 8695623668 | Unit-III | Quality | To reduce the Avg Variation of Basicity of Sinter Plant 1 from 0.08 to 0.04 . | Variation | 0 | 0.08 | 0.04 | 0 | 0 | Week 1 - Wednesday | Completed | Completed | Completed | NA | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 11 | 16027 | Arijit Modi | 6292234402 | JSBIL | Commercial | To Reducing the Despatch cycle time from --- hrs to ---- hrs of Jai salasar. | 0 | 0 | 0 | 0 | 0 | 0 | Week 1 - Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | Completed | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 12 | 45143 | Arun Thatoi | 9333923391 | Unit-IV | Central Electrical | Increase Average Load Factor of Unit-IV from 72.49 % to >80 % per Day | Average Load Factor/Day | % | 72.49 | 80 | 7.51 | 885 | Week 1 - Wednesday | Completed | 0 | 0 | 0 | 0 | Completed | Completed | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 13 | 4924 | Ashok kumar Singh | 9674389400 | Unit-III | Industrial Relationship | Increase the Contractual Manpower engagement of Unit-III from ---- per month to 100 % . | Manpower Engagement | % | 0 | 100 | 0 | 0 | Week 1 - Wednesday | Completed | Completed | Completed | NA | Completed | 0 | Completed | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 14 | 49844 | Ashutosh Pathak | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Week 1 - Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | Completed | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 15 | 80428 | Atish Gupta | 9889202226 | Mackeil | Sales & Marketing | Improve on time Delivery of Finished Goods in Mackeil per month from 43 to 56%. | On time Delivery | % | 43 | 56 | 0 | 156 | Week 1 - Wednesday | Completed | Completed | Completed | NA | Completed | Completed | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 16 | 6389 | Avinash Kumar Mahato | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Week 1 - Wednesday | 0 | Completed | Completed | Completed | Completed | 0 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 17 | 464 | Binoy Kumar Vishwakarma | 9749166676 | Unit-III | Sinter Operation | Reduce the specific energy consumption per ton of sinter from 299634 to <284652 Kcal/TS. | Specific energy consumption | Kcal/TS | 299887 | <284652 | 0 | 200 | Week 1 - Thursday | Completed | Completed | Completed | NA | Completed | Completed | Completed | NA | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 18 | 7799 | Kamal kant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Week 1 - Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 19 | 7780 | Hilary Joseph | 8797990355 | Unit-III | Industrial Relationship | Reducing Manpower cost /MT 4.58 cr from 3.67 cost/MT | Manpower cost | Cost/MT | 4.58 | 3.67 | 0 | 1112 | Week 1 - Friday | Completed | 0 | 0 | 0 | 0 | Completed | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 20 | 5612 | Manoj Kumar | 9332025013 | Unit-III | Safety | Reducing Mandays loss of Jai Balaji Unit-3 from 1546 per month to 600 per /month | Mandays loss per month | Days | 1546 | 600 | 0 | 32 | Week 2 - Monday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 21 |  | Nagendra singh | 0 | Unit-III | MBF Operation | Increase the Avg Productivity of MBF2 per day from 3.2 Ton/m3 to >3.606 Ton/m3 . | Productivity | Ton/m3 | 2.3 | 2.8 | 0 | 1350 | Week 2 - Tuesday | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 0 | 1 | 0 | 0 | 0 | 0 | 1
B1 | 22 | 10590 | Babu Swadesh Sharma | 0 | 0 | 0 | 0 | Increased EBITDA | 0 | 0 | 0 | 0 | 0 | Week 1 - Thursday | Completed | 0 | 0 | 0 | 0 | Completed | Completed | 0 | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 23 | 334 | Bidyut Bikash Dinda | 9832024881 | Unit-III | Coke Oven Mechanical | Reduce the average monthly general Maintenance Cost per ton of Coke Oven Plant from ₹28.6 to <₹25. | Maintenance Cost | ₹/Ton | 28.6 | 25 | 0 | 13 | Week 1 - Thursday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 24 | 48356 | Gourav Sarkar | 8983747047 | Unit-IV | Business Excellence | Reduce Average Specific Power Consumption of Induction Heater Per Day from 41 to 25. | Specific power Cons. | Kwh/MT | 41 | 25 | 0 | 144 | Week 1 - Thursday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 27 | 49096 | Goutam Patel | 7857998919 | Unit-IV | Business Excellence | Reduce the specific power Consumption of Furnace-2 per day from 4251 kWh/MT to 3700 kWh/MT of Ferro Alloys. | Specific power Cons. | Kwh/MT | 4251 | 3700 | 0 | 558 | Week 1 - Thursday | Completed | Completed | Completed | NA | Completed | Completed | Completed | 0 | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 28 | 16407 | Manas Mukherjee | 9434081809 | Unit-I | Ferro Operations | Reduce the Avg Specific power consumption from 3954 KWH/MT to 3558 KWH/MT for Furnace-1 . | 1.SP Consumption | Kwh/MT | 3954 | 3558 | 0 | 202 | Week 1 - Friday | Completed | Completed | Completed | NA | Completed | Completed | Completed | 0 | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 29 | 16407 | Manas Mukherjee | 9434081809 | Unit-I | Ferro Operations | Increase the Avg Metal recovery(High SiMg) from 83.48% to 90 % for Furnace-1. | 2.Metal Recovery | % | 83.48 | 90 | 0 | 36.5 | Week 1 - Friday | Completed | Completed | Completed | NA | Completed | Completed | Completed | 0 | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 30 | 16407 | Manas Mukherjee | 9434081809 | Unit-I | Ferro Operations | 3. Metal Recovery from JIG Fine dust of size 0.5mm | 3.Metal recovery from fine dust | % | 0 | 0 | 0 | 0 | Week 1 - Friday | Completed | 0 | 0 | 0 | 0 | Completed | Completed | 0 | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 31 | 7747 | Prasanta Basu | 9348078887 | Unit-III | ISO | Reduction of Paper Consumption through Effective IMS Internal Audits & Competence-Based Training from 27620 to < 5524. | Paper Consumption | Nos | 27620 | 5524 | 0 | 22 | Week 1 - Friday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | Completed | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 32 | 2483 | B.K Mishra | 9332189890 | Unit-III | Coke Oven Operation | Reduce the Ash % in Coke of Coke oven plant per month from 12.84 to <12.5 . | Ash % in Coke | % | 12.92 | 12.5 | 0 | 653 | Week 1 - Friday | Completed | Completed | Completed | Completed | 0 | Completed | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 33 | 2712 | Abdur Rowf | 8798025416 | Unit-III | Store | Reducing Non moving items of Central store values from 6.3Cr. to <3.15Cr. INR | Non moving items Value | Cr | 6.3 | 3.15 | 0 | 315 | Week 1 - Friday | Completed | Completed | Completed | Completed | Completed | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 34 | 8216 | Pankaj Dubey | 9937484666 | Unit-III | Human Resource | Reducing absenteeism in operation Department per month from 10% to <7 %. | Absenteeism % | % | 10 | 7 | 0 | 0 | Week 1 - Friday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 35 | 2954 | Amit Dahari | 9083696960 | Unit-III | MBF Electrical | Reduce the Avg Specific energy consumption of MBF per month from 134.4 kWH/THM to 125 KWH/THM. | Specific Power Consumption | KWH/THM | 134.4 | 125 | 0 | 238 | Week 2 - Monday | Completed | 0 | 0 | 0 | 0 | Completed | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 36 | 6363 | Molay Pan | 9110174522 | Unit-III | Coke Oven Electrical | Reduce Specific energy consumption per day of Coke oven plant from 8.43 kWh/Ton to <7.5 kWh/Ton . | Specific Power Consumption | kWh/Ton | 8.43 | <7.5 | 0 | 0 | Week 2 - Monday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 37 | 2834 | Ashish Ranjan | 7863955305 | Unit-III | DIP Operation | Reducing over all rejection of DIP from 12.7 % to 9.7 % .for K7 & from 9.8 to 6.8 % for K9. | Rejection | % | 12.7 for K7 9.8 for K8 | 9.7 for K7 6.8 for K8 | 0 | 0 | Week 2 - Monday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 38 | 4382 | Prithwis Bhattacharya | 9932102831 | Unit-III | DIP Mechanical | To reduce the frequency of downtime per month on M/C 5,6,7A & 9 from 49 ,38,44,29 to 32,27,31,&20 respectively i.e increase MTBF without increase MTTR. | Downtime Frequency | Nos | 0 | 0 | 0 | 0 | Week 2 - Monday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 39 | 5152 | Somnath Patra | 7066035508 | Unit-III | Sinter Electrical | Reduce the Specific Power Consumption of Sinter Plant 1 from 61kWh/MT to <45 kWh/MT per day. | Specific Power Consumption | kWh/Ton | 52.52 | <45 | 0 | 250 | Week 2 - Monday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 40 | 5733 | Kalyan Lahiri | 9083902440 | Unit-III | Supply Chain Management | Increase the average service cost saving of jai Balaji Industries Ltd Unit-III per month from 17.8 Lakh to 19.58 Lakh. | Cost Saving | Lakh | 17.8 | 19.58 | 0 | 213 | Week 2 - Monday | Completed | Completed | Completed | Completed | Completed | Completed | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 41 | 7855 | Harsh Sharma | 7682963094 | Unit-III | Sinter Mechanical | Reducing Down time per month from 6.81 to < 5 hr for SP1 & from 5.5 to < 3 hr for SP2 | Downtime | hr/month | 6.81 5.50 | 4 2 | 0 | 19.57 | Week 2 - Tuesday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 0 | 0 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 42 | 7448 | Prasanta Karmakar | 9002239322 | Unit-III | RMHS Operation | Increase the average monthly efficiency of Iron ore Washery Plant-1 from 77.25 % to >85% & Iron Ore Washery Plant-2 from 78.26% to 85%. | Efficiency | % | 82.8 80.73 | >85 | 0 | 0 | Week 2 - Tuesday | Completed | Completed | Completed | 0 | 0 | Completed | 0 | NA | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 43 | 5503 | Alok Mandal | 8538934405 | Unit-III | Operation | Reduce the average Gox Venting Loss per month from 339 to 180 MT. | Power Consumption per Heat | kWh/Heat | 6875.9 | <6700 | 0 | 0 | Week 2 - Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 44 | 3413 | Surajit Thakur | 7044511592 | Unit-III | Electrical | Reduce Power Consumption per Heat of Furnace-2 from 6875.9 kWh to <6700 kWh in LCFC Plant. | Power Consumption per Heat | kWh/Heat | 6875.9 | <6700 | 0 | 83.52 | Week 2 - Tuesday | Completed | Completed | 0 | Completed | 0 | Completed | Completed | NA | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 45 | 3927 | Subhash Ghosh | 9083268271 | Unit-III | Civil | Vendor cost optimization | 0 | 0 | 0 | 0 | 0 | 0 | Week 2 - Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 46 | 6095 | B Banerjee | 8920999709 | Unit-III | Drawings and Design | Reduce the Invisible Zn losses of DIP per day from 26.4 to 9.3 gram/m2 . | Invisible loss | Gram/m2 | 26.4 | 9.3 | 0 | 119 | Week 2 - Tuesday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 47 | 3069 | Kamal Bandyopadhyay | 9332132614 | Unit-III | Account | Reduce Avg Planned vs. Actual Cost Variation of the MBF Plantper month from 1449 to 1232. | MBF Cost | Inr/Month | 1449 | 1232 | 0 | 0 | Week 2 - Tuesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 48 | 7313 | Pushpendra Ganguly | 7077756012 | Unit-III | MBF Operation | Increase the Avg Productivity of MBF2 per day from 3.2 Ton/m3 to >3.606 Ton/m3 . | Productivity | Ton/m3 | 3.41 | 3.7 | 0 | 959 | Week 2 - Tuesday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 49 |  | Sandip Sil ,A.P Sahoo,Sudipta Chatterjee | 8910880295 | Unit-III | DIP Operation | Reducing over all rejection of DIP from 12.7 % to 9.7 % .for K7 & from 9.8 to 6.8 % for K9. | Rejection | % | 12.7 for K7 9.8 for K8 | 9.7 for K7 6.8 for K8 | 0 | 421 | Week 2 - Tuesday | Completed | Completed | NA | Completed | Completed | Completed | 0 | Completed | 0 | 1 | 0 | 0 | 0 | 0 | 1
B1 | 50 | 3013 | Samanway Das | 0 | Unit-III | MBF Operation | Reduce the Coke consumption of Blast furnace 2 per day from 499 Kg/THM to 484 Kg/THM. | Fuel Consumption | Kg/THM | 499 | 484 | 0 | 1781 |  | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 51 | 6323 | Nagesh Kumar | 0 | Unit-III | DIP Electrical | Reduce the specific power consumption of DIP Compressor from 52.83 KWH/MT to 35 KWH/MT per day. | Specific power Cons. | Kwh/MT | 52.83 | 35 | 0 | 133 | Week 2 - Wednesday | Completed | Completed | Completed | NA | Completed | Completed | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 52 | 47561 | Mohammad Ahmad | 7719375128 | Unit-IV | Human Resource | Optimize manpower cost of Unit -IV. | 0 | 0 | 0 | 0 | 0 | 0 | Week 2 - Thursday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 53 | 48956 | Sailesh Singh Yadav | 9653062852 | Unit-IV | Operation | Increasing Cr Recovery from 87% to >90% in Ferro alloys division in AOD. | Chrome Recovery | % | 87 | 90 | 0 | 958 | Week 2 - Thursday | Completed | 0 | 0 | 0 | 0 | Completed | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 54 | 9517 | PK Swain | 93320181 | Unit-IV | Electrical | Improving power factor from ------- to -------- in Unit -IV. | 0 | 0 | 0 | 0 | 0 | 0 | Week 2 - Thursday | Completed | 0 | 0 | 0 | 0 | Completed | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 55 | 0 | Arijit Mondal | 0 | Unit-IV | CPP Operations | Increase the Steam Generation rate of 85 TPH Boiler per month from 49 to 76 ton/hrs. | steam generation rate | Ton/hrs | 49 | 76 | 0 | 390 | Week 2 - Thursday | Completed | 0 | 0 | 0 | 0 | Completed | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 56 | 50618 | Sohel Rana | 7551852180 | Unit-IV | Business Excellence | Increasing Yield from -------- to ---------- Improvement in by billet length increase in rolling Mill. | 0 | 0 | 0 | 0 | 0 | 0 | Week 2 - Thursday | Completed | 0 | 0 | 0 | 0 | Completed | 0 | NA | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 57 | 45833 | Papan Nayak | 9331593225 | Unit-IV | CPP Operations | Reduce the Avg Steam loss of Power Plant per month from 8895 to 2261 ton. | Steam | Ton | 8895 | 2261 | 79608 | 937 | Week 2 - Wednesday | Completed | Completed | Completed | NA | Completed | Completed | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 58 | 10952 | Prakash Joshi | 6292325200 | Unit-III | Human Resource | Manpower cost optimization per month from 7.04 cr to 6.8 cr of Unit-III. | Manpower cost | cr | 7.02 | 6.8 | 0 | 300 | Week 2 - Wednesday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 60 | 6388 | Randhir Kumar | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Week 2 - Wednesday | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 61 | 4 | Ravindra Kumar Meherwal | 8332083767 | Unit-III | Central Electrical | Increase the Avg Load factor of LCFC per month(for furnace 1 to 5) from 0.78 to 0.83. | Load Factor | 0 | 0.78 | 0.83 | 0.6 | 349 | Week 2 - Wednesday | Completed | Completed | Completed | NA | Completed | Completed | 0 | 0 | Not Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 62 | 10811 | Roopam Rai | 8900794810 | HO | Business Excellence | Development of New Products with High Demand for Open Die Forgings Plant". | 0 | 0 | 0 | 0 | 0 | 0 | Week 2 - Thursday | 0 | 0 | 0 | 0 | 0 | 0 | Completed | 0 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 63 | 48624 | Sidheswar Biswal | 7004800310 | Unit-IV | Safety | Reducing unsafe condition per months from 406 to < 203. | Unsafe condition | Nos | 406 | 203 | 0 | 0 | Week 2 - Thursday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 64 | 50360 | Pratip Roy | 8697879215 | Unit-IV | Business Excellence | Reducing feeding variance from ------ to -------for yeild improvement . | 0 | 0 | 0 | 0 | 0 | 0 | Week 2 - Thursday | Completed | 0 | 0 | 0 | 0 | Completed | 0 | NA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 65 | 48820 | Kumar Dipendra | 8675606821 | Unit-IV | CPP Operations | Increasing Steam Generation in BF Gas Boiler(free fuel Based) from 21138 Ton/Month to > 24520 Ton/Month | Steam Generation | Ton/Month | 21138 | 24520 | 40584 | 483 | Week 2 - Thursday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B2 | 66 | 48820 | Kumar Dipendra | 8675606821 | Unit-IV | CPP Operations | Increase Flow Rate of DM Plant per month from 12.8 to 18 cu. m/hr & from 598.6 to 1406.3 cu. m for OBR. | Flow Rate | cu. m/Hr | 12.8 | 18 | 0 | 12 | Week 2 - Thursday | Completed | Completed | Completed | Completed | Completed | Completed | Completed | NA | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B1 | 67 | 49269 | Sanjay Nayak | 8373063448 | Unit-IV | Ferro Operations | Improve the Avg Cr recovery % of Ferro Plant 1,2,3 from 84.53 ,80.23, 87.825 per month to 88, 85, 90 per month. | Cr recovery | % | 84.53 ,80.23, 87.825 | 88,85,90 |  |  | Completed | Completed | Completed | Completed | Completed | Not Completed | Completed |  |  |  | 0 |  |  |  |  | 0 |  | 0
B1 | 68 | 69 | Shantimoy Som | 7001985060 | Unit-III | Coke Oven Mechanical | Increase the Avg Coke Oven Gas of Coke Oven plant from 44958 Ton/month to 51836 Ton/month. | Coke oven Gas | Ton | 44958 | 53949 | 107892 | 1285 | Completed | Completed | Completed | NA | Completed | Completed | Completed |  |  |  | 1 |  |  |  |  | 1
Note on AA1: ====== ID#AAAB2trhrZc admin (2025-12-09 11:19:55) List of all Causes
Note on AB1: ====== ID#AAAB2trhrYQ admin (2025-12-09 11:19:55) List of Significant Causes(Hypothesis ) and high risk causes (FMEA)
Note on AC1: ====== ID#AAAB2trhrYU admin (2025-12-09 11:19:55) Relations Diagram and why why analysis
Note on AG1: ====== ID#AAAB2trhrY8 admin (2025-12-09 11:19:55) 3 months data